## Slide 1: AERO 999
Independent Research
Weekly Status Update
Tim Coon
21 March 2014

## Slide 2: Overview
Review Task
Status update
Upcoming Conferences/Papers
Research Review Status
Calendar Review
Open Topics

## Slide 3: Administrative Items
Full-time coursework requirement
12 units: SP14(+0), SU14(+8), FA14(+12)
MECH 622
Enroll in MECH 622 or AERO 899?
Dr. Dillsaver is the MECH 622 professor, should I discuss my arrangement with him?
Notes: ----- Meeting Notes (3/21/14 11:49) -----
Update Ed Plan to get the 12 units in three quarters
Maj Dillsaver
Cobb to follow up with Liebst

## Slide 4: Status Update
Accomplishments since last meeting
    Moved deformable mirror and WaveScope to CTEx lab
      Searched for operations manuals, etc.
      Is there any documentation on the equipment?
    I spoke with Dr Hyde
      He referred me to Troy Ellis at Starfire.
      I find no email for Troy in Global
    SSA Mission (GSSAP)
      Announced by Gen Shelton
      Similar to SBSS, but in a higher orbit
      Primary contractor is Orbital and I emailed VP of strategic development, but received no response
    GEO SSA Research Proposal
Notes: o
----- Meeting Notes (3/21/14 11:49) -----
Ask Jay if he has any documentation for optical equipment
Jim Brown at starfire AFRL/RDS
Isaac Thornton
Orndorff - Former Orbital VP Stategic Development,
GOrndorff@sgt-inc.com
SSA - SMC/SY
Topics: New hardware for better images, then image processing
Environment test bed for optical performance testing. Research existing solutions.
Scenario - model - hardware design - Hardware verification
Scenario - Hardware verification

## Slide 5: Follow Up From Last Meeting

## Slide 6: Upcoming Tasks (1/2)
Literature Review
  Read, compile, and organize optical control papers
Spring Quarter
  OENG 644 Fourier Optics
  MATH 605 Nonlinear Differential Equations
  MECH 622 Functional Optimization (Formally enroll)
  ASYS 765 Robust Control (Audit)
Topic Search
  Should I try to contact Col Walli again?
Notes: ----- Meeting Notes (3/21/14 11:49) -----
burl, jefferey

## Slide 7: Upcoming Tasks (2/2)
Linear model of OAM telescope
  Model as closely as possible and verify the model
  Model disturbances
  Identify misalignments in the model
Zemax Simulation
  Simulate a deformable mirror in Zemax OAM model
  Assess any performance gains changing curvature and, therefore, focal length using deformable mirror for a dynamic observer.
    An SSA telescope might need to observe targets within a significant range of distances. If a deformable mirror is in the system already, then it might be advantageous in changing the focal length of the system. Dr. Hawks agrees that it is worth investigating.
Notes: ----- Meeting Notes (3/21/14 17:38) -----
If nobody has a method to test on-orbit performance of deformable mirror focus length adjustment, then it would be PhD-worthy
check the literature for this niche
possible SY investment
Ask Dr. Ayers about small sat optics performance testing

## Slide 8: Calendar Review
Hard Dates:
Coursework completed: 12 June 2014
Proposed Dates:
Research Statement: 31 July
Qualifying exam: 23-? June 2014
Notes: ----- Meeting Notes (3/21/14 17:38) -----
Pick the committee
20 May - Research statement draft
1 June - Committee request letters

## Slide 9: Research Question Review
  Optimal control of slew maneuver for space-based optics.
  Disturbance rejection in sparse-aperture array.
  Minimum degrees of freedom required for On-orbit alignment of space-based optical array.
  Optical hardware/prescription design considering optimal control in the dynamic environment.

## Slide 10: Task Review (1/1)
Task 1: Literature Review
  Yingling
  Shepherd
  Peterson
  Sobers
  Kyongsoo
  Breckenridge & Redding
    Improve optical state estimation methods
  Ruppel (2011)
    “In the future, concepts for closed-loop system identification of large deformable mirrors have to be developed.”

## Slide 11: Demonstration
Optimal optical prescription considering the dynamic environment