## Slide 1: AERO 999
Independent Research
Weekly Status Update
Tim Coon
14 June 2014

## Slide 2: Overview
Review Task
Status update
Upcoming Conferences/Papers
Research Review Status
Calendar Review
Open Topics

## Slide 3: Follow Up From Committee Meeting
Dr. Black wants me to put him and Dr. Jennings on my committee
Need three faculty committee members

## Slide 4: New Administrative Items
Committee:
  Cobb, Baker, Hawks, Black, Jennings
CTEx Sponsor Visit
  Making visual aids and demonstrations with Hawks
Upcoming events:
  Tonsillectomy, Wednesday, 23 July
  California trip, 12-19 August

## Slide 5: New Tasks (1/1)

## Slide 6: Task Review (1/7)
Task 1: Literature Review
  Breckenridge & Redding
    Analysis and Control of Optical Systems
  Yingling
    SMT quai-static wavefront sensing and control
    Use Yingling’s outlines and techniques as the basis for closing the loop on the dynamic controller
    He uses a lot of software with pre-made models
  Burtz
    SMT fine surface robust control using adaptive optics

## Slide 7: Yingling
Yingling Contributions
My Proposed Contributions

## Slide 8: Task Review (2/7)
Task 2: Summer Quarter
  ASYS 625 Nonlinear Analysis and Control
  AERO 899 Pseudospectral Methods
Notes: ----- Meeting Notes (3/28/14 10:31) -----
1-2 646-116 ASYS 765

## Slide 9: Task Review (3/7)
Task 3: Topic Search
  Close the loop on dynamic control and optical design and structural design
Notes: ----- Meeting Notes (3/28/14 10:31) -----
1-2 646-116 ASYS 765

## Slide 10: Task Review (4/7)
Task 4: Prism System ID
  No new progress

## Slide 11: Task Review (5/7)
Task 5: OAM Model
  PROGRESS:
    Completed forward raytrace model in MATLAB following Breckenridge/Redding method
    Calculated sensitivities
  NEXT:
    Integrate sensitivity calculations into raytrace code
    Apply Yingling’s method to flush out state-space model
Notes:   Linear/Nonlinear OAM model
    Validate model by experiment
    Explore system ID methods
  Slewing and disturbance rejection using SSM and FSM
    Simulation and experiment
    Explore system ID/performance/computation time
  Explore hardware optimization and control optimization methods using stochastic inputs and Monte Carlo analysis
  Compare static hardware design and dynamic hardware design
  PS methods for optimal solution, validate with calculus of variations, and compare with real-time controller (LQR?) performance
    This could probably be a topic on its own

## Slide 12: Task Review (6/7)
Task 6: Zemax Model
  PROGRESS:
    None
  NEXT:
    Simulate a deformable mirror in Zemax OAM model
    Assess any performance gains changing curvature and, therefore, focal length using deformable mirror for a dynamic-range space-based observer
      Especially in an OAM, significant change in focal length via a translation stage causes more risk than a DM

## Slide 13: Task Review (7/7)
Task 7: DM AO
  PROGRESS:
    None
  NEXT:
    Space-Based AO using deformable mirror
      Misalignment in an OAM causes more than just tip/tilt error and will most likely require DM OA to control higher-order wavefront errors caused by slew flexing, vibrations, thermal deformations
      e.g. when I put a slight pressure on the OAP, significant coma/defocus/astigmatism was observed

## Slide 14: Calendar Review
Hard Dates: | 
20 May 2014: | Research Statement Draft
01 June 2014: | Committee Request Letters
12 June 2014: | Coursework completed
31 July 2014: | Finalize Research Statement
? 2014: | Qualifying Exam
Proposed Dates: | 
March 2015 | Prospectus Defense
JULY
AUG
SEPT
OCT
NOV
JAN
FEB
MARCH
Notes: Put together meeting
Specify clear objectives
----- Meeting Notes (5/9/14 15:17) -----
Reasonable research statement by qualifying exam

## Slide 15: Desired Progression
Optical state estimation of prism assy
  Simulation
  Experiment
Linear and nonlinear model of CTEx telescope
Verify CTEx telescope model by experiment
AO for CTEx? If chromatic aberration from lens is causing problems, then what about atmospheric aberrations in terrestrial testing?
Optimize hardware for slewing and jitter control
Optimize hardware for higher-order AO